## Checklist_Master
Tourism Facility Readiness & Reopening Checklist - ensuring safe, standards-based reopening
Category | Checklist Item | Severity | Status | Responsible | Due Date | Notes | Score
Structural Safety | Roof and envelope inspected and secured | Medium | Yes | Engineering | 2025-11-21 |  | 1
Structural Safety | Glazing/doors intact or boarded where required | Medium | Yes | Security | 2025-11-24 |  | 1
Structural Safety | Load-bearing walls and stairs structurally sound | Critical | Yes | Procurement | 2025-11-19 |  | 1
Structural Safety | Flood intrusion assessed and remediated | Critical | Yes | Procurement | 2025-11-21 |  | 1
Structural Safety | Debris cleared from ingress/egress routes | High | Yes | Security | 2025-11-15 |  | 1
Structural Safety | Slip/trip hazards mitigated with signage or repair | Medium | No | Security | 2025-11-18 |  | 0
Fire & Life Safety | Fire alarm and detection tested | High | Yes | Security | 2025-11-21 |  | 1
Fire & Life Safety | Sprinkler or suppression operational | High | Yes | HR | 2025-11-14 |  | 1
Fire & Life Safety | Portable extinguishers inspected and charged | Medium | Partial | Front Office | 2025-11-14 |  | 0.5
Fire & Life Safety | Emergency lighting and exit signage working | Low | Yes | Front Office | 2025-11-20 |  | 1
Fire & Life Safety | Evacuation routes and muster points marked | Low | Partial | Security | 2025-11-17 |  | 0.5
Fire & Life Safety | Drill conducted with duty staff | Critical | Yes | Procurement | 2025-11-18 |  | 1
Utilities: Power/Water/HVAC | Main power restored or generator available | High | Yes | Housekeeping | 2025-11-18 |  | 1
Utilities: Power/Water/HVAC | Generator load test and fuel log in place | High | Yes | Front Office | 2025-11-17 |  | 1
Utilities: Power/Water/HVAC | Potable water quality verified | High | Yes | Engineering | 2025-11-13 |  | 1
Utilities: Power/Water/HVAC | Wastewater system functional and safe | High | Yes | Procurement | 2025-11-13 |  | 1
Utilities: Power/Water/HVAC | HVAC operational with clean filters | Critical | Yes | Engineering | 2025-11-14 |  | 1
Utilities: Power/Water/HVAC | Gas lines inspected and leak tested | Medium | Partial | Security | 2025-11-25 |  | 0.5
WASH: Sanitation & Hygiene | Handwashing stations stocked | High | Yes | Engineering | 2025-11-24 |  | 1
WASH: Sanitation & Hygiene | Housekeeping SOPs updated for post-storm cleaning | High | Partial | HR | 2025-11-14 |  | 0.5
WASH: Sanitation & Hygiene | Disinfectants within expiry and in stock | High | Yes | Procurement | 2025-11-13 |  | 1
WASH: Sanitation & Hygiene | Linen and laundry process validated | Critical | Yes | Procurement | 2025-11-25 |  | 1
WASH: Sanitation & Hygiene | Waste segregation and pickups scheduled | Critical | No | Security | 2025-11-13 |  | 0
WASH: Sanitation & Hygiene | Vector control measures in place | Medium | Partial | Front Office | 2025-11-24 |  | 0.5
Housekeeping & Pest Control | Deep clean complete in guest areas | Critical | Yes | Procurement | 2025-11-15 |  | 1
Housekeeping & Pest Control | Mold inspection and remediation documented | Critical | Yes | Front Office | 2025-11-14 |  | 1
Housekeeping & Pest Control | Pest inspection and baiting completed | High | Yes | HR | 2025-11-17 |  | 1
Housekeeping & Pest Control | Cleaning equipment tested and safe | Medium | No | HR | 2025-11-20 |  | 0
Housekeeping & Pest Control | Back-of-house cleaned and organized | High | Partial | Front Office | 2025-11-25 |  | 0.5
Housekeeping & Pest Control | Chemical storage secured and labeled | Medium | Partial | HR | 2025-11-21 |  | 0.5
Food & Beverage Safety | Walk-ins and cold chain within temperature range | Medium | Partial | Front Office | 2025-11-16 |  | 0.5
Food & Beverage Safety | Food stock triaged and spoiled items discarded | Medium | No | Front Office | 2025-11-18 |  | 0
Food & Beverage Safety | Water/ice used for F&B is potable | Critical | Yes | Security | 2025-11-14 |  | 1
Food & Beverage Safety | Kitchen hoods and gas cut-offs functional | Medium | Partial | Front Office | 2025-11-20 |  | 0.5
Food & Beverage Safety | HACCP logs restarted and verified | High | No | Engineering | 2025-11-25 |  | 0
Food & Beverage Safety | Staff hygiene refresher completed | Low | Yes | Front Office | 2025-11-14 |  | 1
Pools, Spas & Recreation | Pool structure and fencing safe | High | No | Procurement | 2025-11-25 |  | 0
Pools, Spas & Recreation | Water chemistry within safe ranges | Medium | Yes | Housekeeping | 2025-11-25 |  | 1
Pools, Spas & Recreation | Circulation/filtration operational | Low | Yes | Front Office | 2025-11-24 |  | 1
Pools, Spas & Recreation | Lifeguard/first aid equipment available | High | Yes | HR | 2025-11-20 |  | 1
Pools, Spas & Recreation | Playground/fitness equipment inspected | Medium | No | IT | 2025-11-22 |  | 0
Pools, Spas & Recreation | Spa operations water quality validated | High | No | Front Office | 2025-11-17 |  | 0
ICT & Digital Continuity | PMS/POS online with recent backups | Medium | Yes | IT | 2025-11-20 |  | 1
ICT & Digital Continuity | Wi‑Fi coverage tested in guest areas | Low | Partial | IT | 2025-11-23 |  | 0.5
ICT & Digital Continuity | Cybersecurity checks and patching done | High | Yes | Housekeeping | 2025-11-21 |  | 1
ICT & Digital Continuity | Offline check‑in/out contingency prepared | Medium | Yes | Engineering | 2025-11-22 |  | 1
ICT & Digital Continuity | Emergency contact trees updated in system | Medium | Partial | Engineering | 2025-11-21 |  | 0.5
ICT & Digital Continuity | Payment terminals operational | High | Yes | Security | 2025-11-18 |  | 1
Security & Access Control | Perimeter lighting and CCTV operational | High | Yes | Security | 2025-11-20 |  | 1
Security & Access Control | Key control and access systems tested | High | Partial | IT | 2025-11-20 |  | 0.5
Security & Access Control | 24/7 security staffing coverage planned | Medium | Yes | Front Office | 2025-11-25 |  | 1
Security & Access Control | Visitor/vendor sign‑in procedures active | Low | Partial | Front Office | 2025-11-15 |  | 0.5
Security & Access Control | Cash handling secure routes defined | High | Partial | Engineering | 2025-11-23 |  | 0.5
Security & Access Control | Incident reporting channel tested | Medium | Yes | F&B | 2025-11-19 |  | 1
Staff Health & HR Readiness | Return‑to‑work roster confirmed | Critical | Partial | Front Office | 2025-11-15 |  | 0.5
Staff Health & HR Readiness | Transport and scheduling solved for staff | Medium | Yes | Security | 2025-11-13 |  | 1
Staff Health & HR Readiness | Health screening or fit‑for‑duty checks | Critical | Partial | IT | 2025-11-23 |  | 0.5
Staff Health & HR Readiness | PPE available where tasks require | Medium | Partial | F&B | 2025-11-17 |  | 0.5
Staff Health & HR Readiness | Psychosocial support information shared | Critical | Partial | Security | 2025-11-15 |  | 0.5
Staff Health & HR Readiness | Training refreshers completed | High | Partial | Front Office | 2025-11-19 |  | 0.5
Guest Services & Communications | Pre‑arrival email with status and FAQs | Critical | Yes | Engineering | 2025-11-25 |  | 1
Guest Services & Communications | Visible safety signage and in‑room info | High | Yes | Security | 2025-11-18 |  | 1
Guest Services & Communications | Flexible booking and cancellation terms | High | Yes | F&B | 2025-11-25 |  | 1
Guest Services & Communications | Complaint handling and escalation defined | High | Yes | Front Office | 2025-11-15 |  | 1
Guest Services & Communications | Accessibility routes verified | High | No | Procurement | 2025-11-22 |  | 0
Guest Services & Communications | Multilingual materials available | High | Yes | Housekeeping | 2025-11-20 |  | 1
Supply Chain & Vendors | Priority vendor list verified | Critical | Yes | Housekeeping | 2025-11-16 |  | 1
Supply Chain & Vendors | Alternative suppliers identified | High | Yes | Front Office | 2025-11-24 |  | 1
Supply Chain & Vendors | Delivery windows and routes confirmed | Medium | Yes | HR | 2025-11-19 |  | 1
Supply Chain & Vendors | Fuel and critical spares inventory buffered | Medium | Yes | HR | 2025-11-18 |  | 1
Supply Chain & Vendors | Local producer linkage re‑established | Critical | Yes | Front Office | 2025-11-15 |  | 1
Supply Chain & Vendors | Contracts and SLAs updated | Critical | Yes | Security | 2025-11-18 |  | 1
Environmental & Waste | Beach/grounds debris cleared and disposed | Medium | Partial | IT | 2025-11-17 |  | 0.5
Environmental & Waste | Stormwater drains cleared and functional | High | Partial | Housekeeping | 2025-11-23 |  | 0.5
Environmental & Waste | Hazardous waste handled correctly | High | Yes | Front Office | 2025-11-18 |  | 1
Environmental & Waste | Noise/dust controls during repairs | Medium | Partial | Front Office | 2025-11-14 |  | 0.5
Environmental & Waste | Erosion control where needed | Medium | Partial | Housekeeping | 2025-11-23 |  | 0.5
Environmental & Waste | Biodiversity-sensitive areas protected | Critical | Yes | HR | 2025-11-14 |  | 1
Transport & Excursions | Shuttle/taxi partners vetted and briefed | Critical | Yes | Housekeeping | 2025-11-24 |  | 1
Transport & Excursions | Vehicle inspections and insurance current | Critical | Yes | Housekeeping | 2025-11-16 |  | 1
Transport & Excursions | Marine/water tours safety checks complete | Critical | Partial | Front Office | 2025-11-19 |  | 0.5
Transport & Excursions | Temporary route maps for guests ready | Critical | Partial | HR | 2025-11-14 |  | 0.5
Transport & Excursions | Accessibility transport options available | High | Partial | F&B | 2025-11-19 |  | 0.5
Transport & Excursions | Excursion operator readiness verified | Medium | Yes | F&B | 2025-11-13 |  | 1
Finance, Insurance & Cashflow | Insurance claims filed with documentation | Medium | No | Housekeeping | 2025-11-25 |  | 0
Finance, Insurance & Cashflow | Business interruption tracked | High | Partial | HR | 2025-11-15 |  | 0.5
Finance, Insurance & Cashflow | Cashflow forecast and runway defined | High | Yes | Engineering | 2025-11-23 |  | 1
3. Tourism Facility Readiness & Reopening Checklist - ensuring safe, standards-based reopening. | Supplier payment plan agreed | Critical | No | Front Office | 2025-11-20 |  | 0
Finance, Insurance & Cashflow | Point‑of‑sale and petty cash controls checked | High | No | IT | 2025-11-25 |  | 0
Finance, Insurance & Cashflow | Emergency procurement rules communicated | High | Partial | IT | 2025-11-25 |  | 0.5
Compliance, Permits & Inspections | Building and occupancy permits validated | High | Yes | HR | 2025-11-14 |  | 1
Compliance, Permits & Inspections | Health inspection scheduled/completed | Low | Yes | IT | 2025-11-14 |  | 1
Compliance, Permits & Inspections | Fire inspection scheduled/completed | Medium | Partial | HR | 2025-11-13 |  | 0.5
Compliance, Permits & Inspections | Pool/spa permits validated | Medium | No | HR | 2025-11-18 |  | 0
Compliance, Permits & Inspections | Food handling permits validated | Critical | Yes | F&B | 2025-11-13 |  | 1
Compliance, Permits & Inspections | Reopening certificate requested/issued | High | Yes | HR | 2025-11-16 |  | 1

## Readiness_Scoring
Category | Score | Weight | Weighted Score
Compliance, Permits & Inspections | 0.75 | 0.02 | 0.015
Environmental & Waste | 0.66667 | 0.05 | 0.033333
Finance, Insurance & Cashflow | 0.33333 | 0.03 | 0.01
Fire & Life Safety | 0.83333 | 0.1 | 0.083333
Food & Beverage Safety | 0.5 | 0.08 | 0.04
Guest Services & Communications | 0.83333 | 0.06 | 0.05
Housekeeping & Pest Control | 0.66667 | 0.06 | 0.04
ICT & Digital Continuity | 0.83333 | 0.06 | 0.05
Pools, Spas & Recreation | 0.5 | 0.05 | 0.025
Security & Access Control | 0.75 | 0.06 | 0.045
Staff Health & HR Readiness | 0.58333 | 0.06 | 0.035
Structural Safety | 0.83333 | 0.1 | 0.083333
Supply Chain & Vendors | 1 | 0.05 | 0.05
Transport & Excursions | 0.75 | 0.05 | 0.0375
Utilities: Power/Water/HVAC | 0.91667 | 0.09 | 0.0825
WASH: Sanitation & Hygiene | 0.66667 | 0.08 | 0.053333

## Overall_Score
Overall Readiness Score
0.73333

## Staff_Roster
Name | Role | Training Completed | PPE Issued | Shift
Staff 01 | Supervisor | Yes | Yes | B
Staff 02 | Lifeguard | No | No | B
Staff 03 | F&B | Yes | Yes | A
Staff 04 | Supervisor | Yes | Yes | B
Staff 05 | F&B | Yes | Yes | A
Staff 06 | Front Desk | Yes | Yes | B
Staff 07 | Housekeeping | Yes | Yes | B
Staff 08 | F&B | Yes | Yes | A
Staff 09 | F&B | Yes | No | A
Staff 10 | Supervisor | Yes | Yes | A
Staff 11 | F&B | Yes | No | A
Staff 12 | Maintenance | Yes | Yes | A
Staff 13 | F&B | Yes | Yes | B
Staff 14 | Housekeeping | Yes | Yes | A
Staff 15 | F&B | Yes | Yes | A
Staff 16 | Maintenance | Yes | Yes | A
Staff 17 | Lifeguard | Yes | Yes | A
Staff 18 | Housekeeping | No | Yes | B
Staff 19 | Maintenance | Yes | Yes | A
Staff 20 | Front Desk | Yes | Yes | B
Staff 21 | Lifeguard | No | Yes | B
Staff 22 | Front Desk | No | Yes | B
Staff 23 | Supervisor | No | No | A
Staff 24 | Front Desk | Yes | Yes | B
Staff 25 | Lifeguard | Yes | Yes | B
Staff 26 | Supervisor | No | Yes | B
Staff 27 | Maintenance | Yes | Yes | A
Staff 28 | Maintenance | No | Yes | B
Staff 29 | Front Desk | Yes | Yes | B
Staff 30 | Supervisor | Yes | Yes | B
Staff 31 | Front Desk | No | Yes | B
Staff 32 | F&B | Yes | Yes | A
Staff 33 | F&B | Yes | Yes | B
Staff 34 | Security | No | Yes | A
Staff 35 | Front Desk | Yes | Yes | A
Staff 36 | Front Desk | Yes | Yes | A
Staff 37 | Front Desk | No | Yes | B
Staff 38 | Security | No | Yes | A
Staff 39 | F&B | Yes | Yes | B
Staff 40 | Housekeeping | Yes | Yes | A

## Utilities_Log
System | Status | Last Check | Notes
Power | Grid Restored | 2025-11-11
Generator | Operational | 2025-11-11
Water | Potable Verified | 2025-11-10
Wastewater | Functional | 2025-11-10
HVAC | Running | 2025-11-11
Gas | Leak-free | 2025-11-09

## Inventory_Supplies
Item | Unit | Par Level | On Hand | Reorder Point | Supplier
Diesel Fuel | L | 2000 | 1600 | 1200 | FuelCo
Disinfectant | L | 50 | 60 | 25 | CleanPro
Gloves | Box | 20 | 25 | 10 | SafeHands
Masks | Box | 20 | 15 | 10 | SafeHands
Pool Chlorine | kg | 30 | 22 | 15 | AquaChem
Food Staples | kg | 200 | 180 | 150 | Local Co-op

## Reopen_Plan
Task | Owner | Start | Finish
Deep clean guest areas | Housekeeping | 2025-11-13 | 2025-11-16
Repair glazing and minor roofing | Engineering | 2025-11-14 | 2025-11-22
Test fire systems and drills | Security | 2025-11-15 | 2025-11-17
Water potability and pool chemistry | Engineering | 2025-11-14 | 2025-11-18
Kitchen deep clean and HACCP reset | F&B | 2025-11-13 | 2025-11-17
Generator load test and fuel stock | Engineering | 2025-11-13 | 2025-11-15
Staff refresher training | HR | 2025-11-13 | 2025-11-19
Guest communications pack | Front Office | 2025-11-14 | 2025-11-16
Pre-opening walkthrough | Management | 2025-11-17 | 2025-11-18
Soft opening | All | 2025-11-19 | 2025-11-21

## Incident_Log
Date | Type | Brief | Action | Owner | Status

## Vendor_List
Vendor | Service | Primary Contact | Alt Contact
FuelCo | Fuel | +1-000-111 | +1-999-111
CleanPro | Cleaning Chemicals | +1-000-222 | +1-999-222
AquaChem | Pool Chemicals | +1-000-333 | +1-999-333
Local Co-op | Food Supplies | +1-000-444 | +1-999-444
TechNet | IT Support | +1-000-555 | +1-999-555

## Category_Weights
Category | Weight
Structural Safety | 0.1
Fire & Life Safety | 0.1
Utilities: Power/Water/HVAC | 0.09
WASH: Sanitation & Hygiene | 0.08
Housekeeping & Pest Control | 0.06
Food & Beverage Safety | 0.08
Pools, Spas & Recreation | 0.05
ICT & Digital Continuity | 0.06
Security & Access Control | 0.06
Staff Health & HR Readiness | 0.06
Guest Services & Communications | 0.06
Supply Chain & Vendors | 0.05
Environmental & Waste | 0.05
Transport & Excursions | 0.05
Finance, Insurance & Cashflow | 0.03
Compliance, Permits & Inspections | 0.02